## Risk Register
Technical Debt Risk Register
Techstyle Solutions Studio — score every legacy debt item against enterprise impact and remediation difficulty, then let the sheet rank your backlog.
Debt Item | System / Pipeline | Impact (1-5) | Likelihood (1-5) | Risk Score | Remediation Effort | Priority Rank | Notes
Hand-rolled ETL script, no version control | Nightly billing extract | 5 | 4 |  | L |  | The only person who understands it left the team.
Untested SQL views feeding exec dashboard | Executive reporting | 5 | 3 |  | M |  | A silent schema change already broke this once.
Hard-coded credentials in scheduled job | Vendor data sync | 4 | 2 |  | S |  | Security exposure, not just fragility.
No schema enforcement on ingestion | Customer events pipeline | 3 | 5 |  | M |  | Upstream product team ships breaking changes weekly.
Orphaned dbt models with no owner | Marketing attribution | 2 | 3 |  | S |  | Still running, nobody would notice if it broke.
Manual monthly reconciliation spreadsheet | Finance close process | 3 | 4 |  | M |  | Two-day close delay every time it's wrong.
Single-region warehouse, no failover | Core analytics warehouse | 5 | 2 |  | L |  | Acceptable risk today; won't be at current growth rate.

## How to score
How to score this register
Impact (1-5): how much damage this item does if it fails or is exploited — 1 is a minor inconvenience, 5 is a P1 incident or compliance exposure.
Likelihood (1-5): how probable failure is in the next 6-12 months given current usage, load, and change frequency — 1 is unlikely, 5 is near-certain.
Risk Score = Impact × Likelihood (auto-calculated). This is what you triage by, not gut feel.
Remediation Effort: S/M/L — how much engineering time it takes to actually fix, independent of how risky it is. A high-risk, low-effort item is your next sprint.
Priority Rank auto-ranks every row by Risk Score, highest first — use it to order the backlog conversation, not as the only input (a rank-1 item that's also Large effort still needs a resourcing decision).
Built by Techstyle Solutions Studio — techstylesolutions.studio